## Lead
Online Book Review System
Group Number - 3
Team Lead- Kommuru Sravani

## Status Track
Project Status Check Report Team - 7
Sl no. | Employee ID | Name | Domain | Module | 2024-09-12 | 2024-09-13 | 2024-09-14 | 2024-09-16 | 2024-09-17 | 2024-09-18
1 | 2604064 | Kommuru Sravani | Back-end,Front-end | Admin | Analysis on project | User Rate a book | Admin Rating list | PPT Presentation | Junit testing | Unit testing using Postman
2 | 2603930 | M S Barath | Back-end,Front-end | user | User Profile | User Profile | User Profile | Update User Profile | Update User Profile | Update User Profile
3 | 2604543 | Mashitha H M | Back-end,Front-end | Admin | Admin Login Component | Admin Login Component | Admin Login Component | Admin Login Component | Admin Dashboard | Admin Dashboard
4 | 2604492 | Kotyada Sowmya | Back-end,Front-end | user | User Login Component | User Login Component | User Registration | User Registration | User Dashboard | User Dashboard
5 | 2605334 | Kiran Raikar | Back-end,Front-end | Admin | Admin and User Booklist | Admin Booklist | User Booklist | Enable Book status | Enable Book status | Search Filter
6 | 2605104 | Kruthik Raj M | Back-end,Front-end | Admin | CRUD Operations-Add Book | CRUD Operations-Add Book | CRUD Operations-Update Book | CRUD Operations-Update Book | CRUD Operations-Delete Book | CRUD Operations-Delete Book
7 | 2604624 | Kannammai M | Back-end,Front-end | user | Database creation | Home page | Home page | - | - | -

## Status Meeting
Status Meeting Group - Name
Meeting Date | Time | Progress Check | Time | Problem Solving | Time | Collaboration
2024-09-12 | 9:30 | a | 2:30 | a | 18:20 | a
2024-09-13 | 9:30 | a | 1:00 | a | 6:20 | a
2024-09-14 | 9:30 | a | 2:00 | a | 6:10 | a
2024-09-16 | 9:30 | a | 3:00 | a | 6:30 | a
2024-09-17 | 9:30 | a | 1:30 | a |  | a
2024-09-18 | 9:30 | a | 2:30